## Sheet1
| Task (Group 3) | Date | Team Member(s)
Mathematical Representation formulation |  | 2021-03-26 | Nate Eitel, Casey Myers, Gabriel Gamez
Subtask | Finding Relevant Equations
Obtain Transfer Function for system
Convert mathematical representation to matlab/simulink |  | 2021-04-02 | Clinton Merrit, Brandon Nowack
Subtask | Develop Outline of Code Logic
Convert Equation to transfer function
Create Website |  | 2021-04-09 | Gabriel Gamez
Subtask | Choose Domain Name
Research themes and formatting
Skeletonize web page
Begin connection of Matlab to Copellasim |  | 2021-04-09 | Clinton Merrit, Brandon Nowack
Subtask | Copellasim Tutorials
Build Model
Implement reaction wheel in Copellasim |  | 2021-04-19 | Clinton Merrit, Brandon Nowack
Subtask | Begin to define model behavior
Run simulation test of model behavior
Fill out technical documentation of Website |  | 2021-04-23 | Nate Eitel, Casey Myers, Gabriel Gamez
Subtask | Skeleton of Technical Document
Format Mathematical representation for report
Begin report format |  | 2021-04-23 | Clinton Merrit, Brandon Nowack
Subtask | Create outline with appropriate headings.
Begin Listing References
Finalize simulation including testing |  | 2021-05-07 | Clinton Merrit, Brandon Nowack
Subtask | Confirm model behaves in predicted fashion
Record Final Model Demonstration
Complete report |  | 2021-05-14 | Nate Eitel, Casey Myers, Gabriel Gamez, Clinton Merrit, Brandon Nowack
Subtask | Update Report based on Results
Insert Final Images, Results, etc.
Complete power point |  | 2021-05-14 | Nate Eitel, Casey Myers, Gabriel Gamez, Clinton Merrit, Brandon Nowack
Subtask | Update Report based on Results
Insert Final Images, Results, etc.
Format and submit all deliverables |  | 2021-05-14 | Nate Eitel, Casey Myers, Gabriel Gamez, Clinton Merrit, Brandon Nowack
Subtask | Check for consistency of fonts, spelling, and content
Final Review of Deliverables